## Data Collection Calendar
[PROJECT NAME] - DATA COLLECTION CALENDAR
Fiscal Year: | [FY2024]
Indicator | Method | Tool | Sample | Responsible | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Notes
[Indicator 1.1] | Survey | HH Questionnaire | 385 HH | M&E Officer | Mar: B; Jun: M; Sep: E | B=Baseline, M=Midline, E=Endline
[Indicator 1.2] | FGD | FGD Guide | 6 groups | Program Manager | [12 empty] | Quarterly FGDs | bar: Jan to Dec
[Indicator 2.1] | Admin Data | Health Register | All facilities | Health Officer | [12 empty] | Monthly extraction | bar: Jan to Dec
[Indicator 2.2] | Observation | Checklist | 20 sites | Field Monitor | [12 empty] | Quarterly visits | bar: Jan to Dec
[Indicator 3.1] | KII | Interview Guide | 15 stakeholders | M&E Officer | [12 empty] | Semi-annual | bar: Jun; Dec
[Indicator 3.2] | Assessment | Skills Test | 100 participants | Trainer | Feb: Pre; Jun: Post | Pre/Post training

## Legend
DATA COLLECTION CALENDAR - LEGEND
SYMBOLS:
● = Data collection activity scheduled
B = Baseline data collection
M = Midline data collection
E = Endline data collection
Pre = Pre-intervention assessment
Post = Post-intervention assessment
DATA COLLECTION METHODS:
Survey - Structured questionnaire (household, individual, facility)
FGD - Focus Group Discussion (6-10 participants)
KII - Key Informant Interview (individual stakeholder)
Admin Data - Routine data from registers, records, databases
Observation - Direct observation using structured checklist
Assessment - Skills test, knowledge quiz, performance evaluation
Document Review - Analysis of reports, policies, plans
Monitoring Visit - Site visit for quality assurance
TIPS:
1. Schedule data collection to avoid busy seasons (harvest, holidays)
2. Allow 2-4 weeks for survey preparation before collection dates
3. Plan analysis time after collection (minimum 2 weeks)
4. Align with reporting deadlines (allow 1 month before reports due)
5. Color-code completed activities (green) vs. pending (no fill)